## Slide 1: S/4HANA Finance migration and DB conversion
Bonnie Hohlfeld, Chris Attwood
Auckland NZSUG + SAP Summit 2019

## Slide 2: Agenda
Bonnie Hohlfeld, Chris Attwood
Auckland NZSUG + SAP Summit 2019

## Slide 3: Agenda
Bonnie Hohlfeld, Chris Attwood
Auckland NZSUG + SAP Summit 2019
Overview of the Business
Overview of the SAP Landscape
Project scope and benefits
Project facts and figures
Execution of the migrations
Cutover weekend
Lesson learnt

## Slide 4: Overview of Business
Bonnie Hohlfeld, Chris Attwood
Auckland NZSUG + SAP Summit 2019

## Slide 5
We make sure New Zealanders get more out of life.

## Slide 7
335
stores
22k
people
1.3m
customers every week
$7.9b
sales
In the North Island…

## Slide 8: Overview of SAP Landscape
Bonnie Hohlfeld, Chris Attwood
Auckland NZSUG + SAP Summit 2019

## Slide 9: Overview of the SAP History @ FSNI
Bonnie Hohlfeld, Chris Attwood
Auckland NZSUG + SAP Summit 2019
1996 - Implemented SAP on AS/400 - 3.0F
2001 - Migrated to AIX/DB2 – 4.6C
2008 - SAP rollout to Gilmour’s
2012 - Project Lightening Phase 1 Go-live ECC 6.0 EHP6
2017 - ECC upgrade to EHP8
2018 - Migration of ECC on HANA with S/4 Fin 1605
2019 - All remaining apps migrated to HANA

## Slide 12
SAP Finance modules and add-ons
Accounts
Payable and
Accounts
Receivable
Asset
Accounting
New GL and
Reporting
Project
Systems and
Controlling
Flexible
Real Estate
Management
Open Text VIM
and Agency Business
Cash Management
GLWAND,
GLSU

## Slide 13: Project scope and benefits
Bonnie Hohlfeld, Chris Attwood
Auckland NZSUG + SAP Summit 2019

## Slide 14: Transition Paths
  ECC
  EhP8
Non HANA
  ECC
  EhP8
HANA
  S/4 HANA Finance 1605
HANA
  S/4 HANA
  1709+
HANA
Cust, Vend & Site conv

## Slide 15
Benefits of approach
Platform for further enhancements
Increased SAP system performance
Time savings via transactional efficiencies
Enhanced user experience - fiori apps

## Slide 16: Powerful reporting
FBL1H
FBL5h
FAGLL03H.

## Slide 18: Project facts and figures
Bonnie Hohlfeld, Chris Attwood
Auckland NZSUG + SAP Summit 2019

## Slide 19
6 mths
Duration
10
Workstreams
15
No of migrations
300
Reviewed notes
Key project stats
42hr
Outage
825
Code modifications

## Slide 20
MAY-18
JUN-18
JUL-18
AUG-18
SEPT-18
OCT-18
SANDBOX TESTING
DEV TESTING
QA TESTING
PPRD
POC
CUSTOM CODE REVIEW
PROJECT AND CHANGE MANAGEMENT

## Slide 21: DB Migration
Bonnie Hohlfeld, Chris Attwood
Auckland NZSUG + SAP Summit 2019

## Slide 22
DB migration approach
Migration was incorporated into our “standard” yearly patching cycle.
Minimizing Downtime was a key consideration
Dual Landscape to minimize the impact on BAU and other projects
DB Migration

## Slide 23: Tools – SUM DMO
DB Migration

## Slide 24
Post installation of add-on
New config becomes available
New roles and tcodes
New CDS views and technical tables
No postings are possible until the migration is completed
DB Migration

## Slide 25: S/4HANA Finance activities
Bonnie Hohlfeld, Chris Attwood
Auckland NZSUG + SAP Summit 2019

## Slide 26
Key Finance Activities
Finance Migration.
FI Config
Readiness
Checks
Preparation
Activities.
Validations

## Slide 27: Readiness check continued
Readiness
Checks
Notes: The prerequisites check is an ABAP report that does a preliminary check whether your current system meets the conditions for implementing SAP Simple Finance. This ABAP report is available by SAP Note implementation.

## Slide 28: Readiness check continued
Readiness
Checks
Notes: It

## Slide 29: FI-AA Prerequisite check
Readiness
Checks

## Slide 30: Finance preparation activities
Activate business functions – SFW5
Period end closing
  Asset specific (prior year as well)
  GL specific (completed month-end)
Extract pre-migration validation reports
  GL balances
  Asset balances
  AR and AP balances
Preparation
Activities.

## Slide 31
FI Config

## Slide 32
Key Finance Activities
Finance Migration.
Config and Impacts
Readiness
Checks
Preparation
Activities.
Validations

## Slide 33: Finance Migration Cockpit
Finance Migration.

## Slide 34: Post migration activities
Extract post migration reports
Perform validations and comparisons
Validations

## Slide 35: First run findings
Bonnie Hohlfeld, Chris Attwood
Auckland NZSUG + SAP Summit 2019
Reality did not equal the vision

## Slide 36
Learnings of first run
Sizing
CDS views
Didn’t wait for SAP, did a workaround
Numerous asset issues
Duration 9 days
Sub optimal partitioning

## Slide 37
MAY-18
JUN-18
JUL-18
AUG-18
SEPT-18
OCT-18
ITERATIVE TESTING
SANDBOX TESTING
DEV TESTING
QA TESTING
PPRD
POC
CUSTOM CODE REVIEW
DOWNTIME PREP
LEGACY LOADS & ASSET REGISTERS
PROJECT AND CHANGE MANAGEMENT

## Slide 39: Iterative Tests
Bonnie Hohlfeld, Chris Attwood
Auckland NZSUG + SAP Summit 2019
If at first, you don’t succeed, dust yourself up and try again, try again ..

## Slide 40: Move to Iterative testing
Migration testing needed production sized hardware!
Allowed ongoing development of the migration while COE teams continued to deliver work
We were able to asses the effect of the limited variables available to us
Allowed us to build a body of knowledge around SUM DMO / SAP HANA and FINMIG screens, across the team.
DB Iterative Tests

## Slide 41: Iterative testing: Key migration Variables (1)
HANA Parameters – SAP HANA Parallelism / Delta Merge
HW sizing – Need production like HW to do meaningful testing
Data volumes – Archiving data had significate influences on runtime, in particular the cluster tables which are converted
  CDCLS -> CDPOS converted to 12 billion rows
  KOCLU -> KONV converted to 14 billion rows
  COEP had more than 3 billion rows and this triggered a code rewrite by SAP
DB Iterative Tests

## Slide 42: Iterative testing: Key migration Variables (2)
# of Migration streams : 5 threads per CPUs – 480 was our sweet spot
  we peaked at 6GB/sec output on our MSSQL server NIC
Use a history file for the table splits – to decrease the export/import “tail”
Created Primary keys on cluster table targets before they where loaded.
Run SAP HANA in OVERWRITE Mode for the import
Increase of parallelism in MS SQL from 1 to 4
DB Iterative Tests

## Slide 43
FI Migration Iterative Tests
Number of jobs
Adjusting jobs on the fly +/-
Monitor each step SAP trace
Review load balancing packages

## Slide 44: Cutover weekend
Bonnie Hohlfeld, Chris Attwood
Auckland NZSUG + SAP Summit 2019
.

## Slide 45
Downtime Management
Identified key BO’s
Socialize the outage time
Detailed plan to track progress
Critical process solutions

## Slide 46
Shift Schedule for the 42 hours
Senior Stakeholder Support
Checkpoints and Go-no go decision points
Hour by hour plan to track against
.

## Slide 47: Cut-over weekend

## Slide 48: “…this project was described as being the new benchmark for all Projects to measure themselves against ” Peter Muggleston, CIO 2018
Bonnie Hohlfeld, Chris Attwood
Auckland NZSUG + SAP Summit 2019

## Slide 49
Lessons Learnt
Make use of the available
SAP services
Repetition
Order Production Hardware early
Spring Clean your Database.

## Slide 50: SAP Services and Tools
Near Zero Downtime (NZDT)
Expert on Demand
Going Live Service
OS / DB
Migration
Service
Code Inspector
ABAP SQL Monitor

## Slide 51: Platform for further enhancements
Continued deployment of S/4HANA Finance apps
Embedded reporting – real-time
Data aging
SAP Analytics Cloud
KNOA

## Slide 52: Any questions? Thank you
26 April 2018
Finance Users
52
Thank you!
Notes: Thank you for joining us and we leave you with an African proverb as the Thought for the day.
“If you want to go fast, go alone. If you want to go far, go together”